## Slide 1: Co-ordinating project tasks
Gantt charts
Notes: This could be used during the lesson when discussing Gantt charts.
It is advised to rehearse using these slides, especially the animations on slide 4.

## Slide 2: Example project
Task | Length (days) | Dependencies
A | 2 | -
B | 2 | A
C | 3 | B and F
D | 2 | C
E | 2 | D
F | 3 | A
G | 2 | E and H
H | 2 | D
A dependency is a task that must be completed before the next task can begin…
E.g. task C cannot start until tasks B and F have finished.

## Slide 3: Gantt chart
 | Days |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tasks |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
 | A |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | B |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | C |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | D |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | E |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | F |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | G |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | H |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 4: Gantt chart
 | Days |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tasks |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
 | A |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | B |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | C |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | D |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | E |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | F |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | G |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | H |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Time allocated to the project is shown here.
Brief description of tasks is given here.
Tasks B and F cannot start until task A is completed.
Tasks B and F can start together.
Each bar shows the amount of time allocated to the task.
The whole project is allocated 14 days.